## glimsview_1.0_bugs
| List of Bugs and Desired Features for GLIMSview 1.0. Compiled and maintained by Deborah Lee Soltesz & Bruce Raup. |  |  |  |  | 2026-07-30 03:34
i | Issue ID | Type | Description | Date Reported | Reported by | Platform | Severity | Status | Date Fixed | Fixed by | Notes on Fix | Related URL | Relation | Notes
2 | 1 | Bug | Tool: IP Place point. A glacier ID shows up in the glacier config tab. CTRL-Z (undo) makes the input point go away on the image, but the ID doesn't go away from the glacier config tab. |  | Raup | Linux | Urgent | Closed | 2004-12-06 | dls | adding highlighting of selected points, lines, or glacier ids in list fixed this problem |  | 1
2 | 2 | Bug | Help->About: version number is not current. Says 0.99 instead of 1.0 |  | Raup | Linux | Urgent | Closed | 2004-04-14 | dls
2 | 3 | Bug | User's Guide: There is a link to the GLIMS website, but clicking on it only makes the User's Guide window go blank, and I get the message: "QTextBrowser: no mimesource for http://www.glims.org/" in the terminal window. |  | Raup | Linux |  | Closed | 2004-04-14 | dls | removed link to GLIMS website - the help window is not a true web browser
2 | 4 | Bug | Config:Image -- The image filename is not filled in. |  | Raup | Linux | Urgent | Closed | 2005-08-20 | dls | 4/14/04 - There's still an issue with reading/writing data to the project file. This element has been renamed from filename to Image URL, which is what should be displayed in the dialog. 8/20/2005 - missing & caused data structure holding the data to "lose" it |  | 83
| 5 | Wanted Feature | Glimsview is designed to be run from the installation directory only. If it is run from somewhere else, it doesn't know where to find the pixmaps for the buttons. Should use an environment variable such as GLIMSVIEW_HOME. |  | Raup | Linux |  | Open |  |  |  | http://www.glims.org/glimsview/bug_report/bug005.html
| 6 | Wanted Feature | Ability to export the ASTER (or whatever) image in GeoTIFF, PNG, and other formats. |  | G. Hamilton |  | Urgent | Open |  |  |  |  | 21
| 7 | Wanted Feature | When saving a project, it would be good if the stretches that had been applied to the image were also saved. |  | Raup | Linux |  | Open |  |  |  |  | 96 | relation based on need for project XML refinement and additions
| 8 | Wanted Feature | Should be able to use GCPs to adjust the geolocation of the image, or, ideally, orthorectify the image. |  | G. Hamilton |  |  | Open
2 | 9 | Wanted Feature | When the user tries to exit the program without first saving work, the dialog should be something like "Save before quitting?", and the buttons should say something like "yes", "no", "cancel", where "cancel" cancels the quit operation. |  | Raup |  |  | Closed | 2005-08-04 | dls
| 10 | Wanted Feature | Generic shapefile import: currently, shapefiles must be in lat/lon coordinates. Need to be able to import shapefiles in projected coordinates. |  | Khalsa | Windows | Urgent | Open
1 | 11 | Interface improvement | Bulk delete of polylines, e.g. shift-click to select entire line, DEL key deletes. |  | Khalsa | Windows | Urgent | Open |  |  |  |  | 1
1 | 12 | Interface improvement | Bulk nudge of points (select group of points, move them all together) |  | Khalsa | Windows | Urgent | Open |  |  |  |  | 1
| 13 | Wanted Feature | Autosave/recover feature |  | Khalsa, F. Rau | Windows | Urgent | Open
| 14 | Wanted Feature | Layer manager (things like toggling all lines on and off, or just certain line types on and off) |  | Khalsa | Windows |  | Open | [5 empty] | Multiple layers with photoshop/illustrator style box would be nice, wouldn't it?
| 15 | Wanted Feature | Generic shapefile import without pre-loaded image (requires redesign of program, which currently bases geolocation on a single image) |  | Khalsa | Windows |  | Open | [5 empty] | Doubt a redesign is in order… just a couple tweaks.
2 | 16 | Wanted Feature | Add units to form for inputting glacier params (width, length, area, etc.) |  | Khalsa | Windows | Urgent | Closed | 2005-08-04 | dls
| 17 | Wanted Feature | Prompt before overwrite shapefiles (export) |  | Khalsa | Windows |  | Open
2 | 18 | Wanted Feature | More screens to supply all the metadata that is in the shapefiles it generates. Currently, it gives you the option to input only some of the parameters, but others, like whether the image was orthorectified (segments table) and what the RC_ID is (currently given arbitrary value?) would have to be supplied by editing the shapefiles. |  | Khalsa | Windows | Urgent | Closed | 2006-01-23 | dls | 8/5/2005 - RC_ID and other Session stuff fixed - more fixes coming 1/23/2006 - several Image metadata fields added, fixed Image URL, and added validator button for Acquisition Date-Time |  | 83
2 | 19 | Bug | Occasional crashes; cause unknown; crashes when working on large projects also reported; |  | F. Rau | Windows | Urgent | Closed | 2005-07-14 | dls | refactored undo to not save a copy of the entire line set, reducing memory usage |  | 78 | Probably related to the undo facility creating a full snapshot, which uses a lot of memory for large projects (see also 78)
| 20 | Wanted Feature | Ability to import older Landsat imagery (TM? MSS?) |  | F. Rau | Windows |  | Open |  |  |  |  | 21 | P. Geissler has expressed a need for this also (7/20/2005)
| 21 | Wanted Feature | Ability to import imagery from ASTER L2 |  | F. Rau | Windows |  | Open |  |  |  |  | 21
| 22 | Wanted Feature | Ability to import imagery from SPOT |  | F. Rau | Windows |  | Open |  |  |  |  | 21
| 23 | Wanted Feature | Ability to import imagery from ERS |  | F. Rau | Windows |  | Open |  |  |  |  | 21
| 24 | Wanted Feature | Ability to import imagery from ERDAS Imagine, IDRISI, PCI. (Should currently be able to go through GeoTIFF, though. --B. Raup) |  | F. Rau | Windows |  | Open |  |  |  |  | 21
| 25 | Wanted Feature | Should be able to view georeference system of input imagery (projection, datum) |  | F. Rau | Windows | Urgent | Open |  |  |  |  | 21
2 | 26 | Interface improvement | No project information is available during an analysis session => project name in the program bar, readable session log (translation of the XML file as text or HTML for human readers?), etc. would be extremely helpful for the analyst. |  | F. Rau | Windows | Urgent | Closed | 2006-01-23 | dls |  |  | 69 | 8/2005 - problems getting this to work in windows
2 | 27 | Interface improvement | Save and export options open the same pop-up window without further indication what is to be saved or exported (include specific standard file extensions?). What is the difference between PROJECT => INGEST => IMPORT and IMPORT shapefile? |  | F. Rau | Windows | Urgent | Closed | 2005-08-04 | dls | 8/4/2005 - Changed menu wording - need to add filters to all file boxes
2 | 28 | Interface improvement | More self-explaining menus or a context-sensitive help functions |  | F. Rau | Windows |  | Closed | 2005-08-04 | dls | updated a lot of the menus and icons to be a little more friendly |  | 28
1 | 29 | Interface improvement | On-line help should include GLIMS-specific glossary |  | F. Rau | Windows |  | Open |  |  | 1/23/2006 - added quite a bit to the User Guide; plan to add context-sensitive help in the near future |  | 28 | maybe link to data dictionary?
1 | 30 | Interface improvement | There are some items in the menus which are not explained (histogram best fit, etc.). (This should be improved in on-line help and the manual/tutorial. -B.Raup) |  | F. Rau | Windows |  | Open |  |  |  |  | 28 | would like to totally redesign the histogram functions
2 | 31 | Interface improvement | The icons in the icon bar should be arranged in groups with spacers between (e.g. to avoid the selection of the glacier ID tool between the digitizing tools and the selection tool). |  | F. Rau | Windows |  | Closed | 2005-08-04 | dls | separated the tool buttons by function |  | 31 | need general improvement of icons (see work done by 2005 Capstone team)
| 32 | Interface improvement | Imported shapefiles should be integrated as a grouped item with their arc-specific properties to facilitate a easy identification and a rapid removal of the item from the current session. (This is similar to Item 14, Layer Manager. -B.Raup) |  | F. Rau | Windows |  | Open |  |  |  |  | 14
| 33 | Interface improvement | The selection tool does not provide specific modes for selecting and it is sometimes a little bit tricky to select the different items (points, arcs, glacier Ids). In particular, the individual selection of overlapping arcs is almost impossible. Therefore, it would be great to have a type-sensitive selection tool or at least, the possibility to choose between various tools for selecting the different items. In addition, it is rather difficult to select several items (by pressing the shift button) and to group them (this is required e.g. for the preparation of two connected or neighboring glaciers sharing a common boundary line). |  | F. Rau | Windows |  | Open |  |  |  |  | 33
| 34 | Interface improvement | Determining Left/Right sides of a line needs to be automated, say, by clicking on the side of the line you mean, rather than remembering the direction of digitization. |  | F. Rau, F. Cawkwell, B. Raup | Windows | Urgent | Open | [5 empty] | See series of e-mails on the subject (March 2005). Need some kind of visual feeback on line direction.
2 | 35 | Interface improvement | Should be able to select a glacier and edit its ID, etc. by clicking on the dot associated with the glacier ID. That is, should be able to click on outline and have corresponding ID highlighted in glacier config tool. Conversely, should be able to click on glacier ID in config tool and see which outlines are associated with it. Once the user has done "Set Lines", there is currently no way to see confirmation of that association. |  | F. Rau, B. Raup | Windows | Urgent | Closed | 2004-12-06 | dls |  | http://www.glims.org/glimsview/bug_report/bug035.html | 1
0 | 36 | Interface improvement | Should be able to delete a glacier ID by selecting its ID in the Glacier Config tab of the Configuration dialog. (You can delete a glacier ID by selecting the dot on the image, then pressing the DEL key. -B.Raup) |  | F. Rau | Windows |  | Open |  |  | Tried 12/6/2004 and did not succeed, but know how to fix |  | 1 | See code for notes - tried to fix, but need to create a custom listview object to catch the key strokes
1 | 37 | Interface improvement | There seems to be no access to the characteristics of a digitized feature => it would aid the analysis process if the program provides a direct possibility to extract the information (e.g. via a context sensitive info window, a status bar, or by highlighting the respective feature type in the configuration menu). |  | F. Rau | Windows |  | Open
| 38 | Interface improvement | A tool for measuring length and width of the glacier could facilitate a direct determination of these parameters within an analysis session. |  | F. Rau | Windows |  | Open |  |  |  |  | 38
2 | 39 | Bug | Population of mandatory fields for submission to NSIDC needs to be enforced by GLIMSview. See related URL for list. |  | Raup | Linux | Urgent | Open |  |  | 1/23/2006 - current work on "consistency" is working towards this goal | http://www.glims.org/MapsAndDocs/datatransfer/data_transfer_specification.html | 96 | Combination of GLIMSView enforcement and completed & correct Schema or DTD; 8/4/2005 - An additional cross-reference list has been compiled based on the data dictionary, the Schema updated - need to go through GV to check for inconsistencies and make sure data entry fields are the appropriate size
2 | 40 | Bug | Image Info Tab: ?Acquisition? is misspelled. |  | Raup | Linux |  | Closed | 2004-04-14 | dls
2 | 41 | Bug | Tools->Plugins: ?Threshold? is misspelled. |  | Raup | Linux |  | Closed | 2004-04-16 | dls
| 42 | Bug | GLIMSview doesn't read geolocation information from GeoTIFF. |  | Raup | Linux | Urgent | Open
2 | 43 | Bug | Null values need to be handled consistently for exporting. |  | Raup | Linux | Urgent | Open |  |  | 1/23/2006 Need to find out what Bruce means by this |  | 96 | is this a related issue to storage of WGMS values? Which NULL values are inconsistent? My vote is -1 means undefined
1 | 44 | Wanted Feature | DEM: Ability to do 3-dimensional analysis, using imagery and a DEM. |  | A. Racoviteanu |  |  | Open |  |  |  |  | 95 | P. Geissler has reasserted this need, along with anaglyph/stereo viewing (95)
-1 | 45 | Wanted Feature | Should be able to read attribute data in from a .dbf file |  | F. Cawkwell | Windows | Urgent | Open |  |  | 2007-06-21 fixed GLIMS shapefile import, but not regular shapefile import… |  | 45
| 46 | Wanted Feature | Should be able to read attribute data in from a .xls file (or .sxc file (openoffice spreadsheet format) -B.Raup) |  | F. Cawkwell | Windows |  | Open |  |  |  |  | 45
| 47 | Wanted Feature | Ability to include area of internal rocks in glacier basin in config. |  | F. Cawkwell | Windows |  | Open
| 48 | Wanted Feature | Allow line endpoints to be joined to line midpoints and snap overlapping lines to each other. |  | F. Cawkwell | Windows |  | Open | [5 empty] | Joining to midpoints? Is that valid?
2 | 49 | Wanted Feature | Read shapefiles of points and lines, not just polygons |  | F. Cawkwell | Windows |  | Closed | 2008-05-29 | dls | 2008-05-29 added points import, made both segments and points bring in attributes from DBF file and match to GLIMS project data
| 50 | Wanted Feature | Read in metadata from other formats |  | F. Cawkwell | Windows |  | Open |  |  |  |  | 45
0 | 51 | Bug | In Configuration dialog, the line color selection is not always saved. |  | F. Cawkwell | Windows | Urgent | Open |  | dls | 4/14/04 - haven't been able to repeat problem yet |  | 83
2 | 52 | Wanted Feature | Change color of glacier ID dot when ID is selected in Config |  | F. Cawkwell | Windows |  | Closed | 2004-12-06 | dls |  |  | 1
| 53 | Wanted Feature | Be able to generate an ID for each polygon automatically, and enter automatically into Config. |  | F. Cawkwell | Windows |  | Test | 2004-12-06 | dls | Not fixed, but I believe selecting a glacier ID from the config dialog makes that the default ID for new lines
2 | 54 | Bug | Be consistent in defining longitude as +- 180 or 0-360 |  | F. Cawkwell | Windows | Urgent | Open? | [5 empty] | going with +/-180 (did this get fixed or not?)
1 | 55 | Wanted Feature | Ability to change the order of glacier IDs in the Config list |  | F. Cawkwell | Windows |  | Open |  |  |  |  | 1 | fix will be related to making the delete key work in the lists (see Bug 36)
1 | 56 | Wanted Feature | Ability to change the order of line types in Config list. |  | F. Cawkwell | Windows |  | Open |  |  |  |  | 1 | fix will be related to making the delete key work in the lists (see Bug 36)
1 | 57 | Wanted Feature | Be able to delete line types from Config list. |  | F. Cawkwell | Windows |  | Open |  |  |  |  | 1 | fix will be related to making the delete key work in the lists (see Bug 36)
| 58 | Wanted Feature | Change cursor for different functions (particularly magnifiers) |  | F. Cawkwell | Windows |  | Open |  |  |  |  | 31 | general usability issue
1 | 59 | Wanted Feature | Dashed and dotted lines are unable to resolve complex lines so more colours would be helpful |  | F. Cawkwell | Windows |  | Open | [5 empty] | Qt color picker oughta make this easy
2 | 60 | Wanted Feature | Redo facility |  | F. Cawkwell | Windows |  | Closed | 2005-07-23 | dls | Redo of undo implemented similar to undo. Need to do a little clean-up (abstract upper classes, GID data handled the same as line data, etc.
2 | 61 | Bug | In line definition dialog, ?vegetation? is misspelled. |  | F. Cawkwell | Windows |  | Closed | 2004-05-24 | dls
| 62 | Plug-in | Drainage basin identification plug-in |  | F. Cawkwell | Windows |  | Open
2 | 63 | Bug | Analyst name is not reread into Config/Session tab when reading a previously saved project. Only the "Process Desc" field is reread correctly. Same for image acquisition date in the Image/Info tab. |  | F. Rau, B. Raup |  | Urgent | Closed | 2005-08-04 | dls | All the fields should work correctly now - crashing caused by the "fixes" should also be resolved (8/20/2005) |  | 83
| 64 | Bug | When displaying a GeoTIFF image, geodetic coordinates are not (always) displayed correctly. |  | F. Rau, B. Raup | Windows, Linux | Urgent | Open
2 | 65 | Bug | Southern hemisphere glacier IDs are usually (but not always!) incorrectly generated with "N" rather than "S" |  | F. Rau | Windows | Urgent | Closed | 2004-05-07 | dls | 5/7/04: changed GlacierIDDef::toString to use temp variables for lat/lon so mlat/mlon aren't modified in the process of generating a glacier ID string. 5/5/04: Problem was in GLIMSProject::exportGLIMSIngest - called GlacierIDDef::toString(), which converts lat/lon to postive value with N, S identifier… changed order so lat/lon are written to shape file before toString is called
2 | 66 | Wanted Feature | Ability to edit image metadata in Config tool |  | F. Rau | Windows | Urgent | Closed | 2006-01-23 | dls | 8/20/2005 - fixed issues with Image Information config, so should be easy to finish the job 1/23/2006 - Image config and Session mostly complete, but need to check for absolute correctness with data dictionary |  | 83
| 67 | Wanted Feature | Need general comment field for notes about the glacier |  | F. Rau | Windows |  | Open |  |  |  |  | 67
| 68 | Bug | Crash happens when trying to change viewed band combinations midstream through digitization work. | 2004-02-10 | T. Khromova | Windows |  | Open
2 | 69 | Wanted Feature | Project title or identifier should be in GLIMSview window title bar, so that someone can easily use multiple sessions at the same time. | 2004-02-11 | T. Khromova | Windows | Obnoxious | Closed | 2006-01-23 | dls | added to status bar |  | 69 | Add project title to XML. If not defined, use project file name.
2 | 70 | Wanted Feature | Indicate which metadata are optional, which are mandatory. | 2004-02-19 | Khalsa |  | Urgent | Open |  |  |  |  | 83
| 71 | Wanted Feature | Compute length (given a center line), width (also from a certain segment, use snow line?), and area automatically. | 2004-02-19 | Khalsa |  |  | Open |  |  |  |  | 38
| 72 | Wanted Feature | DEM: With an input DEM, offer orthorectification | 2004-02-19 | Khalsa |  |  | Open |  |  |  |  | 95
| 73 | Wanted Feature | STEREO: With ASTER data, offer stereo viewing while drawing lines (using colored glasses) | 2004-02-19 | Khalsa |  |  | Open |  |  |  |  | 95 | Overlapping footprints or DEM?
| 74 | Wanted Feature | Add comments field to segments, or at least to Glacier_Dynamic | 2004-02-19 | Khalsa |  |  | Open |  |  |  |  | 67
| 75 | Wanted Feature | (related to #11) Be able to select additional lines with shift-click | 2004-04-08 | Khalsa |  | Urgent | Open |  |  |  |  | 11
2 | 76 | Wanted Feature | (similar to #32) Importing shapefiles should allow carry-over of attributes defining line types. | 2004-04-08 | Khalsa |  |  | Closed | 2008-05-29 | dls | 2008-05-29 Updated segments shapefile import and added points shapefile import, both look for GLIMS attributes in the DBF file |  | 32
| 77 | Wanted Feature | (similar to #33) Enhanced selection tool ? polygon bounding region rather than just rubber band box | 2004-04-08 | Khalsa |  |  | Open |  |  |  |  | 33 | Will need this for data->text export (92)
2 | 78 | Wanted Feature | GLIMSview is slow with many vertices. Either speed up, or give warning about too many vertices. | 2004-04-08 | Khalsa |  |  | Closed | 2005-07-14 | dls | refactored undo to not save a copy of the entire line set, reducing memory usage |  | 19 | Probably related to the undo facility creating a full snapshot, which uses a lot of memory for large projects (19)
-1 | 79 | Wanted Feature | If there are lines or polygons that are not associated with a glacier ID, GLIMSview should give a warning before exporting for ingest (and even before saving). | 2004-04-08 | Raup |  | Urgent | Open |  |  |  |  | 1
2 | 80 | Bug | Sometime, the ID dots disappear from the view, even tho' the IDs are still in the config tool list. | 2004-04-08 | F. Bown | Windows | Urgent | Closed | 2004-12-06 | dls
2 | 81 | Bug | The glacier ID is not correctly created from the coordinates. It truncates rather than rounding. More importantly, if the coordinate is something like "43.0532", the corresponding part of the ID becomes "43532"; the algorithm to generate the ID doesn't take into account a zero right after the decimal point. (The XML file stores only the coordinates for each glacier, and doesn't explicitly store the ID.) This is related to #65. | 2004-04-14 | B.Raup |  | Urgent | Closed | 2004-04-16 | dls
| 82 | Wanted Feature | be able to specify a default value for all points (preferably of a given line type), rather than having to enter them individually for each segment. | 2004-04-15 | Khalsa |  | Urgent | Open
0 | 83 | Bug | General issues with saving/reading project information to/from project file, starting with "Image Info" configuration dialog - suspect bigger problem. | 2004-04-16 | D.Soltesz |  | Urgent | Open |  |  |  |  | 83
2 | 84 | Bug | WGMS classifications in Edit Glacier ID dialog are shifted by 1, causing wrong descriptions to be associated with the Glacier ID. | 2004-05-05 | B.Raup, F. Rau |  | Urgent | Closed (Mostly - see notes) | 2004-05-24 | dls | Fixed handling of values for the classifications to output WGMS standard values to the project file. Old projects will be automatically "fixed" and tagged with a version date. Schema (draft at this point) has been created. Version Date is pulled from AboutDlg. |  | 96 | Qt does not handle Schema - it does support DTD and insists on having a DOCTYPE in the file… one option is to suffer with it and use Schema, the other is to convert the Schema to DTD. 69 has another XML related issue
2 | 85 | Typo | Confluent in WGMS classification | 2004-05-20 | J. Kargel |  | Annoying | Closed | 2004-05-24 | dls
2 | 86 | Typo | Primary Classification "prim_class" missing underscore when exported to shapefile | 2004-05-02 | B.Raup, F. Rau |  | Annoying | Closed | 2004-05-24 | dls | Fixed output label on export, and check input labels on import for both "primclass" and "prim_class" for backwards compatibility
2 | 87 | Typo | Output GlacType (again) instead of Name in LineData/LineDefSet/LineDefinition | 2004-05-18 | D.Soltesz |  | Annoying | Closed | 2004-05-24 | dls | No backwards fixes implemented
| 88 | Wanted Feature | Secondary classifications? | 2002-05-21 | B.Molnia |  |  | Open | [5 empty] | Needs to be addressed by GLIMS standards folks
0 | 89 | Bug | lineconfig-data set: the global uncertainties values for Y (sometimes also for X) are always set to zero after importing. in the exported file the values are still proper. | 2004-08-03 | D. Riemann (F. Rau) |  |  | Open
2 | 90 | Bug | Certain EDC Aster products appear as "blank" image | 2004-10-08 | E. Lee |  | Urgent | Closed | 2004-10-19 | dls | DN range not set correctly when reading in 16-bit HDF file, resulting in bad autostretch of the data
| 91 | Bug | Switch window display from normal to cascade and back causes crash | 2004-10-21 | E. Lee |  | Annoying | Open
1 | 92 | Wanted Feature | Export selected DN's to text file for use in spreadsheet | 2004-11-01 | E. Lee, J. Kargel |  | Annoying | Open | [5 empty] | need selection lasso metioned in 77
| 93 | Wanted Feature | When reading NLAPS format, it would be nice it GLIMSview didn't care which file in a set of NLAPS file for a particular image you picked -- it should just know that if you pick a .l? file, you meant the set of files associated with that one. | 2004-11-16 | B. Raup |  | Very Annoying | Open | [5 empty] | Barring a fix, it would at least be good to document that fact that you need to select the .H1 file.
0 | 94 | Bug | Update glacier id list highlighting after doing a Set Line | 2004-12-06 | D. Soltesz |  | Urgent | Open |  |  |  |  | 1 | Hope to fix with other listview issues mentioned in other bug/wish list items
| 95 | Wanted Feature | STEREO: Anaglyph viewing; Load same band into multiple channels; Load Aster 3B with other bands; allow view rotation to take advantage of Aster stereo pairs | 2005-07-20 | P. Geissler, D. Soltesz |  | Suggestion | Open |  |  |  |  | 95 | Similar requests already on list
| 96 | Wanted Feature | Need Schema against which a project file can be validated (by GV) | 2004-05-27 | D. Soltesz |  |  | Open |  |  |  |  | 96 | Work started. Qt 2.3 doesn't handle Schema. Waiting for next version of Qt. May consider switching XML i/o over to use SAX libraries instead of Qt XML module
| 97 | Wanted Feature | Make GV project independent instead of glacier specific; Build dialogs from XML "project description" file that sets fields, types, values, ranges, etc. from project's data dictionary; | 2004-11-01 | D. Soltesz, K. Mullins (Mars Dune DB project) |  | Need by 2007 at the earliest | Open | [5 empty] | 2005 CS Capstone Project worked on this issue, creating dialog boxes on the fly (a la Isis 3) from XML.
2 | 98 | Bug | Prosc_desc truncated to 200 characters | 2005-07-14 | F. Rau |  | Urgent | Closed | 2005-08-04 | dls | 3D description also fixed to save as many characters as is in the description field |  |  | Truncated in XML or shapefile? See e-mail from 7/14
| 99 | Wanted Feature | In the whole view window make it so that whenever you click on the image, with any tool, it moves the red box to that area. Since no other tools can be used in the whole view this would make for less tool switching between the differnt views. | 2005-07-15 | D. Gaseau |  |  | Open |  |  |  |  | 99
| 100 | Wanted Feature | Red box... in any of the views, when the hand tool is selected, make it so that instead of moving the entire image (if the hand tool is clicked outside of the redbox). Make it so the redbox jumps to the place where the user clicked. | 2005-07-15 | D. Gaseau |  |  | Open |  |  |  |  | 99 | Refer to Envi for an example of this functionality
| 101 | Wanted Feature | I am having a hard time selecting points at 2000 zoom to modify them. The selection tool only moves along the pixels and some of my points are not on a pixel boundry, making it hard to select the point that I want. | 2005-07-15 | D. Gaseau |  |  | Open |  |  |  |  | 33
2 | 102 | Bug | Undo doesn't deal with updating the GIDDefSet and thus the list of GIDs doesn't get properly updated on an undo/redo | 2005-08-04 | D.Soltesz |  | Urgent | Closed | 2005-08-05 | dls
2 | 103 | Bug | Export causes crash | 2005-08-05 | F. Rau, I. Brown |  | Show Stopper | Closed | 2005-08-20 | dls | Prior changes to description fields caused issues
2 | 104 | Bug | Export causes crash | 2005-11-01 |  |  | Show Stopper | Closed | 2005-12-01 | dls | Same bug as 104 - update to latest version fixed problem
2 | 105 | Bug | RCID limited to two digits | 2005-11-29 | B. Raup |  | Annoying | Closed | 2006-01-06 | dls | Bad programmer missed reading the full RC ID spec. RC ID increased to 3 digits to cover all possible RC IDs.
| 106 | Wanted Feature | GLIMSView nodes less sensitive to being moved when splitting the line segments | 2005-11-16 | B. Raup, F. Cawkwell |  | Annoying | Open
2 | 107 | Bug | Importing session info from GLIMS ingest shapefile tries too fill info into analyst name and time fields | 2005-11-16 | B. Raup, F. Cawkwell |  | Urgent | Closed | 2006-01-23 | dls |  |  |  | 1/6/2006 - Having issues importing GLIMS shapefiles exported from glimsview (Windows)
-1 | 108 | Wanted Feature | Remove imported shapefiles without touching other work | 2005-11-16 | B. Raup, F. Cawkwell |  | Annoying | Open |  |  |  |  | 14
| 109 | Bug | Configure plug-in crash? | 2006-01-03 | E. Liszewski |  | Annoying | Open
| 110 | Wanted Feature | User profile (automatically loads profile into session) | 2005-11-23 | B. Raup, Matt |  |  | Open | [5 empty] | Would help drastically with keeping session information consistent